## Register
Wild Trout Trust Project Risk and Opportunity Register 2022 V1
|  | Project ref: | Snake Lane Fish Passage |  |  | Total estimated risk to Client | 0 |  | Key Objectives
|  | Updated: | 2022-04-25 |  |  | Total estimated risk to Designer | 0 |  | 1 | Implementation of fish passage improvement design
|  | By: | TJ |  |  | Total estimated risk to Contractor | 0 |  | 2 | Efficient and timely delivery of works
|  | Current stage | Detailed Design |  |  | Estimated total | 0 |  | 3 | Long-term improvement of habitat
ID | Risk/Opportunity | Key Objective | Description | Status | Stage risk/opportunity may arise | Mitigation/realisation measures | Stage measures will be employed | Actioned by | Estimated cost (£) | Residual owner | Risk to Client | Risk to Principle Designer | Risk to Principle Contractor
1 | Risk | 1 | Erosion of bank upstream of weir due to deepening of channel. Scour up\down stream. | Open | Construction | Inspection by Geomorphologist/Structural Engineer when works commence and incorporate bank stabilisation into works. | Construction | Principle Designer |  | Principle Contractor
2 | Risk | 2 | Existing concrete structure has defects (some already visible) below water line which are exposed during works. | Open | Construction | Repair of the existing structure when it becomes visible. | Construction | Principle Designer |  | Principle Contractor
3 | Risk | 2 | Stability of wing walls reduced by notching weir. | Open | Construction | Structural engineer (GCA) to inspect and instruct any additional works when works commence | Construction | Principle Designer |  | Client
4 | Risk | 2 | Concrete specification inadequate over long term; future deterioration. | Open | Post-construction | GCA reviewed with Wild Trout Trust, and agreed to base specifications on previous successful projects undertaken by the EA with Fishtek Consulting. | Construction | Principle Contractor |  | Client
5 | Risk | 2 | Concrete jointing is inadequate over long term; future deterioration. | Open | Construction | Structural engineer (GCA) to develop jointing detail based on assumed construction, and review when cofferdam is in place. GCA to develop in-principle drawing. | Construction | Principle Designer |  | Client
6 | Risk | 2 | Bad weather (up to yellow weather warning conditions) slow or delay works | Open | Construction | Additional time/resources required to deliver works - allow for 1 week delay/lost productivity | Construction | Principle Contractor |  | Principle Contractor |  |  | 0
7 | Risk | 2 | Severe weather (amber or red weather warning) slow or delay works | Open | Construction | Additional time/resources required to deliver works, by prior agreement - allow for 1 week delay/lost productivity | Construction | Principle Contractor |  | Client | 0
8 | Risk | 2 | Out-of bank flooding resulting in temporary or long-term stand down | Open | Construction | Stand-down and remobilise once site conditions allow, with associated cost - allow for demob/remob costs | Construction | Principle Contractor |  | Client | 0
9 | Risk | 2 | Unexpected utilities/services not shown in pre-works services checks, slow or delay works | Open | Construction | Changes to site traffic plan or additional ground protection required | Construction | Principle Contractor |  | Principle Contractor |  |  | 0
10 | Risk | 1 | Unexpected utilities/services not shown in pre-works services checks, prevent delivery of an element of works | Open | Construction | Alteration of detailed design, with associated costs | Construction | Principle Contractor |  | Principle Contractor |  |  | 0
11 | Risk | 2 | Protected species not identified by pre-works surveys, slow or delay work | Open | Construction | Additional time/resources required to deliver works | Construction | Principle Designer |  | Principle Designer |  | 0
12 | Risk | 1 | Protected species not identified by pre-works surveys, prevent delivery of an element of works | Open | Construction | Alteration of detailed design, with associated costs | Construction | Principle Designer |  | Principle Designer |  | 0
13 | Risk | 3 | Works fail to achieve desired habitat improvement | Open | Post-construction | Additional/remedial works required | Post-construction | Principle Designer |  | Client | 0
14 | Risk | 2 | Insufficent or unknown bridge load rating at SK 33897 43487 | Open | Construction | Temporary bridge or bridge reinforcement works | Construction | Principle Contractor |  | Principle Contractor |  |  | 0
15 | Opportunity | 1 | Contractor identifies opportunity to enhance design pre-construction | Open | Detailed Design | Alteration of detailed design, with associated costs | Detailed Design | Principle Designer |  | Principle Designer |  | 0
16 | Opportunity | 1 | Contractor identifies opportunity to enhance design during construction | Open | Construction | Additional time/resources required to deliver works, by prior agreement | Construction | Principle Contractor |  | Client | 0
17 | Opportunity | 2 | Contractor identifies opportunity to improve efficiency pre-construction | Open | Detailed Design | Alteration of detailed design, with associated costs | Detailed Design | Principle Designer |  | Principle Designer |  | 0
18 | Opportunity | 2 | Contractor identifies opportunity to improve efficiency during construction | Open | Construction | Additional time/resources required to deliver works, by prior agreement | Construction | Principle Contractor |  | Principle Designer |  | 0
19 | Risk | 2 | BoQ is inaccurate to +/- 10% | Open | Construction | Additional/fewer materials required, with associated cost/saving | Construction | Principle Contractor |  | Principle Contractor |  |  | 0
20 | Risk | 2 | BoQ is inaccurate to > +/- 10% | Open | Construction | Additional/fewer materials required, with associated cost/saving, if obtained by prior agreement | Construction | Principle Contractor |  | Client | 0
21 | Opportunity | 2 | Gravels won during excavation | Open | Construction | Reduces volume of imported gravel | Construction | Principle Contractor |  | Client | 0
22 | Risk | 1 | Unstable Banks | Open | Construction | Bank erosion during construction, requiring additional works | Construction | Principle Contractor |  | Client | 0
23 | Risk | 1 | Delays to permits/licences | Open | Detailed Design | Pre-construction delays prevent works starting on time; need to accelerate works | Construction | Principle Contractor |  | Client | 0
24 | Risk | 1 | Ground protection required | Open | Construction | Allowance for 150m of Trakmat if ground conditions require | Construction | Principle Contractor |  | Client | 0
25 | Risk | 1 | Reinstatement due to poor ground conditions | Open | Construction | Ground conditions are poor and require additional reinstatement due to rutting - allow 1 day | Construction | Principle Contractor |  | Principle Contractor |  |  | 0

## Lists (hidden)
Riskt/opportunity | Key Objective | Status | Stage risk/opportunity may arise | Stage measures will be employed | Measures to be actioned by | Estimated cost | Owner | Cost to Client | Cost to P. Designer | Cost to P. Contractor
Risk | 1 | Open | Outline Design | Outline Design | Client |  | Client
Opportunity | 2 | Closed | Detailed Design | Detailed Design | Principle Designer |  | Principle Designer
| 3 |  | Construction | Construction | Principle Contractor |  | Principle Contractor
|  |  | Post-construction | Post-construction